## XG766_A0_Qual_plan
[25 empty] | 2017 |  |  | 2018
|  |  | ww04 | ww05 | ww06 | ww07 | ww08 | ww09 | ww10 | ww11 | ww12 | ww13 | ww14 | ww15 | ww16 | ww17 | ww18 | ww19 | ww20 | ww21 | ww22 | ww23 | ww24 | ww25 | ww50 | ww51 | ww52 | ww01 | ww02 | ww03 | ww04 | ww05 | ww06 | ww07 | ww08 | ww09 | ww10 | ww11 | ww12 | ww13 | ww14 | ww15 | ww16 | ww17 | ww18 | ww19 | ww20 | ww21 | ww22 | ww23 | ww24 | ww25 | ww26 | ww27
|  | Qualification schedule for XG766 A0 | [22 empty] | A6.1 | +1 | +2 | +3 | +4 | +5 | +6 | +7 | +8 | +9 | +10 | +11 | +12 | +13 | +14 | +15 | +16 | +17 | +18 | +19 | +20 | +21 | +22 | +23 | +24 | +25 | +26 | +27 | +28 | +29 | Qualification description | voltage bias | Pattern required | JEDEC standard | Comments
| Milestones | A0 Tape-in
A0 samples availability (A6.1) | bar: 2017 ww50 A6.1
B0 Tape-in | bar: 2018 ww17 +19
Required A0 samples for Qualification
| TP prep | Sort test program for Q1 | bar: 2018 ww05 +7
TestB TP (ESD/LU) | bar: 2018 ww01 +3
Test-Q2: (HTOL/THC/…) | bar: 2018 ww13 +15
Si Qual | ESD/LU | ESD HBM 1kV, test to fail | [52 empty] | ESD human body model | no | no | JESD22 | bar: 2018 ww06 +8 to 2018 ww09 +11
|  | ESD CDM 250V IO, 500V Supply test to fail | [52 empty] | ESD charged device model | no | no | JESD22 | bar: 2018 ww06 +8 to 2018 ww09 +11
|  | Latch Up 1.5*Vdd nom, 100mA@Tmax (>70C) | [52 empty] | latch up | yes | yes | JESD78 | latchup tester has limited power rails and tester channels. At design phase need check whether available latchup tester resource ok: - power rail enough if Soc has many power domains - latchup pre-condition pattern is simple and vector less than 512K | bar: 2018 ww06 +8 to 2018 ww09 +11
|  | HTOL (500h) | [52 empty] | High temperature operating life (HTOL) test is to determine the reliability of products by accelerating thermally activated failure mechanisms. Customer parts are subjected to elevated temperatures under biased operating conditions. Typically, dynamic signals are applied to the devices under stress. The typical Vcc is the maximum operating voltage. The test is used to predict long term failure rates. All test samples must pass final electrical test prior to HTOL testing. Applicable Specs: JESD22-A108, MIL-STD-883 Method 1005.8, EIAJ-ED4701-D323 | yes | yes | JESD22 | HTOL pattern need cover following: - scan to cover digital part - mbist to cover array - HSIO covered by loopback - GPIO covered by bscan toggling - if embeded DRAM, also need write/read DRAM During design phase, also need check HTOL tester resources. For complex Soc design limited HTOL tester resource will be bottleneck: - DFT better to design special htol mode for scan reducing required tester channel; | bar: 2018 ww14 +16 to 2018 ww16 +18
HTOL (1000h) | bar: 2018 ww17 +19 to 2018 ww19 +21
HTOL corner 1000h 1.2xVopmax @Tj 125C | bar: 2018 ww14 +16 to 2018 ww24 +26
|  | ELFR(TA > 125°C or TJ > 125°C VCC > 1.2 x Vcc Max) | [52 empty] | screen out potential early life failures | yes | yes | JESD22 | same board and pattern as HTOL but different stress condition and readout?? | bar: 2018 ww17 +19 to 2018 ww20 +22
|  | HTS (150C/1000h) | [52 empty] | The high-temperature storage life test measures device resistance to a high-temperature environment that simulates a storage environment. The stress temperature is typically set to 125°C or 150°C to accelerate the effect of temperature on the test samples. In the test, no voltage bias is applied to the devices. Applicable Specs: JESD22-A103, MIL-STD-883 Method 1008 | no | no | JESD22 | bar: 2018 ww14 +16 to 2018 ww21 +23
PKG Level | Package related tests | Pre-Conditioning | [52 empty] | Preconditioning is to measure the resistance of non-hermetic surface mount devices to worst-case moisture absorption followed by one cycle of the soldering process and two cycles of rework. A statistical sample of parts is inspected with an acoustic microscope before and after preconditioning. Before they undergo the temperature humidity bias test, the temperature cycle test, the thermal shock test, the pressure cooker test or the highly-accelerated temperature and humidity stress test, surface mount devices are subjected to preconditioning and must later pass a final electrical test. Applicable Spec: JESD22-A113 | no | no | JESD22 | bar: 2018 ww06 +8 to 2018 ww08 +10
|  | TC -55 to +125C 700cyc, every 250cyc upto 2000 or fail | [52 empty] | Temperature cycle testing accelerates fatigue failures within a specific die and packaging system. Typical failure mechanisms include die cracking; package cracking, wire bond failure, and first or second level interconnect solder fatigue. The temperature cycling is done in one, two, or three chamber systems that control the air temperature and ramp rate. Ten different temperature conditions and four different soak modes are specified, and the combination of temperature condition and soak mode depends on customer requirements. Applicable Specs: JESD22-A104, MIL-STD-883 Method 1010.7 | no | no | JESD22 | bar: 2018 ww06 +8 to 2018 ww17 +19
|  | THB on live die (1000h) 85% ,85℃ | [52 empty] | The temperature-humidity-bias test is an environmental test designed to accelerate corrosion and dendritic growth. This is an alternative to the High Temperature and Humidity Stress Test (HAST). Although bias is applied, the part is typically put in a low power state to accelerate the failure mechanisms of interest while minimizing self-heating. The duration of the test is 1008 hours, with readouts (final electrical tests) at 168 hours and 504 hours during the test. The stress temperature is 85°C, and the relative humidity is 85%. Testing should be performed no later than 48 hours after the end of ramp-down. The bias voltage is typically the maximum operating voltage. Two kinds of bias may be applied depending on which one is more severe: continuous bias or cycled bias. Samples of surface mount devices must undergo preconditioning and pass a final electrical test prior the THB test. We have temperature-humidity test chambers that meet the requirements called out in the JESD22-A100D standard including the temperature, relative humidity, and ramp conditions. Please contact us to learn more or submit your product for testing. Applicable Specifications and Standards: JESD22-A100D, EIAJ-IC-121-17 | yes | no | JESD22 | normally use same HTOL board to power-up device. But it is un-clear whether pattern is required to put device in low power mode; ?????? | bar: 2018 ww06 +8 to 2018 ww14 +16
|  | uHAST | [52 empty] | unbiased HAST | no | no | bar: 2018 ww06 +8 to 2018 ww09 +11
Bond Shear/Pull Strength | bar: 2018 ww06 +8 to 2018 ww08 +10
Ball Shear | bar: 2018 ww06 +8 to 2018 ww08 +10
Solderability | bar: 2018 ww06 +8 to 2018 ww08 +10
Physical dimension | bar: 2018 ww06 +8 to 2018 ww08 +10
| BLRT | TCoB ICE | [52 empty] | 2nd level reliability: temperature cycling on board |  |  |  | ATE readout not necessary??? | bar: 2018 ww06 +8 to 2018 ww10 +12
MS ICE | bar: 2018 ww06 +8 to 2018 ww10 +12
RV | bar: 2018 ww06 +8 to 2018 ww10 +12
THD 85C/85% RH, 1000 hrs | bar: 2018 ww06 +8 to 2018 ww14 +16
https://wenku.baidu.com/view/6e405998fc0a79563c1ec5da50e2524de518d0f6.html?from=search
Note on Z5: 12/15/2017
Note on AS6: 4/25/2018 B0 Tape-in

## 2nd_level_reliability
Qualification tests related to 2nd level reliability
The qualifications tests related to 2nd level reliability mainly focus on the solder ball connection between package and printed circuit board (pcb). The tests listed below are not adequate for addressing failure modes in the package itself.
Reliability testing for 2nd level is performed according to international standards. Not all key customers purely rely on these standards, so they request other test methods and test conditions. The qualification teams have to consider these.
Test 9.2 Temperature Cycling On Board (TCOB)
Purpose
Verification that the used materials and their interfaces are stable against the mechanical stress caused by large temperature changes.
This includes the interaction with the printed circuit board and the solder connections.
Method
IPC-9701A
Specifications for Reliability Tests on Board [1]
Quantities
1 lot with 45 daisy chain devices on 3 stress boards
Flow
Solder process on PCB 8 layer test board
Temperature cycling on board with application specific PCB
Notes
This test is destructive.
Mainly daisy chain structures are used for connecting the terminations (solder balls, leads, …).
This stress test is designed and operated for observing wear out mechanisms.
For new technologies and studies of new failure modes:
The quantity of performed cycles shall be extended that a cumulated failure rate of 50% is reached.
The failure rate data shall be fitted to a Weibull distribution and the failure mode, which is relevant for the first fails shall be determined.
Nokia test conditions (different quantities, stress boards and cycling conditions) are not used for customer Microsoft[2].
Read out
continuous monitoring during stress
Pass criteria
Inline test of daisy chains:
<20%
no fail for the first
cycles

## B0
|  | 2018 | [26 empty] | 2019
|  | ww26 | ww27 | ww28 | ww29 | ww30 | ww31 | ww32 | ww33 | ww34 | ww35 | ww36 | ww37 | ww38 | ww39 | ww40 | ww41 | ww42 | ww43 | ww44 | ww45 | ww46 | ww47 | ww48 | ww49 | ww50 | ww51 | ww52 | ww01 | ww02 | ww03 | ww04 | ww05 | ww06 | ww07 | ww08
| XG766 B0 Plan | A6.1 | +1 | +2 | +3 | +4 | +5 | +6 | +7 | +8 | +9 | +10 | +11 | +12 | +13 | +14 | +15 | +16 | +17 | +18 | +19 | +20 | +21 | +22 | +23 | +24 | +25 | +26 | +27 | +28 | +29 | +30 | +31 | +32 | +33 | +34
Milestones | B0 samples availability (A6.1) | bar: 2018 ww26 A6.1
Fab Ready HVM1 | bar: 2018 ww32 +6
B0 Qual Start | bar: 2018 ww36 +10
A8 Possible
Die Prep | bar: 2018 ww30 +4
PKG VNAT Readiness | bar: 2018 ww32 +6
TestQ1 TP (ESD/PKG Qual) (Class + VCV) | bar: 2018 ww29 +3
ESD/LU | ESD HBM 1kV, test to fail | bar: 2018 ww30 +4 to 2018 ww33 +7
ESD CDM 250V IO, 500V Supply test to fail | bar: 2018 ww30 +4 to 2018 ww33 +7
Latch Up 1.5*Vdd nom, 100mA@Tmax (>70C) | bar: 2018 ww30 +4 to 2018 ww33 +7
Package Qual | Precon (3x Reflow) | bar: 2018 ww30 +4 to 2018 ww32 +6
HTS (150C/1000h) | bar: 2018 ww30 +4 to 2018 ww37 +11
TC -55 to +125C 700cyc, every 250cyc upto 2000 or fail | bar: 2018 ww33 +7 to 2018 ww45 +19
uHAST 110C 85%RH 264h upto 528h | bar: 2018 ww33 +7 to 2018 ww37 +11
THB on live die (1000h) 85% ,85℃ | bar: 2018 ww33 +7 to 2018 ww40 +14
VNAT Ball shear/Bond Shear/Bond Pull/PD | bar: 2018 ww30 +4 to 2018 ww32 +6
Q2 Sort/Assy/ Test | Sort Q2 (HVQK) | bar: 2018 ww34 +8
TestQ2 TP (HTOL/IME/ELFR with HVQK) (Class + VCV) | bar: 2018 ww37 +11
Si Qual | HTOL (500h) 1.2xVopmax @Tj 125C | bar: 2018 ww38 +12 to 2018 ww41 +15
HTOL (1000h) 1.2xVopmax @Tj 125C | bar: 2018 ww42 +16 to 2018 ww45 +19
HTOL corner 1000h 1.2xVopmax @Tj 125C | bar: 2018 ww38 +12 to 2018 ww48 +22
IME/ELFR 20min/48h 1.2xVopmax @Tj 125C ELFR(TA > 125°C or TJ > 125°C VCC > 1.2 x Vcc Max) | bar: 2018 ww41 +15 to 2018 ww44 +18
BLRT | TCoB -40/+85C 1000 cyc | bar: 2018 ww30 +4 to 2018 ww34 +8
MS Upto 10000G, 0.25ms, 1.2 sine, 3 drops per +/- X,Y,Z axis | bar: 2018 ww30 +4 to 2018 ww34 +8
RV Level 5G Freq. 5Hz-500Hz Axis: +/- X,y,Z duration 30 min per axis | bar: 2018 ww30 +4 to 2018 ww34 +8
THD 85C/85% RH, 1000 hr | bar: 2018 ww30 +4 to 2018 ww38 +12
Pilot lot? 1st lot ? What kind of test Program need for each Reliability test ?